## Slide 1: Project Management Toolkit
Welcome to the Project Management Toolkit:
These four templates are designed to be downloaded, customized, and used immediately on your projects.
Do not get bogged down in making them perfect; use them to drive conversations, align your teams, and deliver value.
Notes: HOW TO USE THIS TOOLKIT:
Welcome to the DHA Project Management Toolkit! As a Project Manager, your goal is not to fill out paperwork; your goal is to deliver value to the Defense Health Agency and our patients.
Save a Master Copy: Keep this file clean as your "Master" template. Whenever you start a new initiative, "Save As" and name it for your specific project.
Keep it Simple: These templates are designed for high-impact executive summaries. Do not shrink the font size to cram more words in. If it doesn't fit on the slide, it is too detailed for an executive briefing.
Iterate: A project plan is a living document. Update these slides constantly as your project evolves.

## Slide 2
Problem Statement
Concisely describe the problem this project solves or the opportunity it capitalizes on. What is the "why" behind this effort? What is the issue? What is the magnitude? When did it start? Who is impacted? Where does it occur? Why solve this now?
Project Purpose / Justification
Explain how this project aligns with DHA strategic goals (e.g., improving readiness, enhancing healthcare delivery, lowering costs). What is the expected Return on Investment (ROI) or value to the enterprise?
Key Performance Indicators (Measures) | 
Baseline Measures (If applicable) | Goals
Metric 1: Metric 2: Metric 3: | Metric goals (add goals tied to metrics in the ‘from X (baseline) to Y (goal/target) by Z (time horizon)’ format.
Scope
In-scope: What is within our authorities, what are the first and last steps of the process being improved? Out of Scope: What will not be addressed by the project?
PROJECT TITLE
C2​ (Control and Command)
Project Lead: Project Sponsor: Approval Date: Core Team: Key Stakeholders:
2
As of: {Add date}
SMART Objectives
List 3-5 Specific, Measurable, Achievable, Relevant, and Time-bound goals. What are the success criteria? Objective 1: (e.g., "Reduce average patient check-in wait times by 20% within 6 months of kiosk implementation.") Objective 2: (e.g., "Achieve an 85% kiosk utilization rate by patients within 90 days of go-live.") Objective 3: (e.g., "Train 100% of front-desk administrative staff on the new system before go-live.")
High Level Deliverables
List 3-5 High-Level Deliverables. Deliverable 1: (e.g., “...") Deliverable 2: (e.g., “….") Deliverable 3: (e.g., “….")
High-Level Risks
Risk 1: (e.g., "Global supply chain issues may delay kiosk hardware delivery.") Risk 2: (e.g., "Administrative staff may exhibit resistance to adopting the new technology.") Risk 3:
Notes: TOOL #1 GUIDANCE: THE CHARTER
Purpose: To officially authorize the project, secure the PM’s authority, and lock in the boundaries of the scope before work begins.
SECTION-BY-SECTION GUIDANCE:
1. Problem Statement: Define the current pain point or gap in one concise sentence. Avoid describing the solution here; focus only on the negative impact currently being felt (e.g., "Manual check-in processes are causing a 15-minute delay in patient throughput at MTF-X").
2. Project Purpose / Justification: This is your "Business Case." Explain why this project is a priority. Explicitly link it to the DHA Strategic Plan or Quadruple Aim. Why should the Agency spend money and time on this instead of something else?
3. Scope: Establish the boundaries. Clearly state what is In-Scope (the work you are committed to) and Out-of-Scope (related items that you will NOT be doing). This is your primary defense against scope creep.
4. SMART Objectives: Define what "Done" looks like. Objectives must be Specific, Measurable, Achievable, Relevant, and Time-Bound. (e.g., "Implement kiosk system at MTF-X by September 30th").
5. Command and Control: Define the governance structure. Who is the Executive Sponsor with signature authority? Who is the Project Manager? Who is on the Project Core Team? Who are the Key Stakeholders?
6. High-Level Deliverables: List the tangible "things" that will be handed over at the end of the project (e.g., "10 installed kiosks," "Staff training manual," "MHS GENESIS Integration bridge").
7. High-Level Risks: Identify the "Project Killers." What are the top 2-3 strategic uncertainties that could derail the timeline or budget before you even begin? (e.g., Hardware supply chain delays or lack of clinical buy-in).
8. Key Performance Indicators (KPIs): How will the Sponsor know the project was successful after the deliverables are handed over? (e.g., "20% reduction in lobby wait times" or "90% patient satisfaction rating").

## Slide 3: Plan of Actions & Milestones (POAM) Template
This template is best implemented in Excel or MS Project for dynamic tracking. This slide serves as a structural model.
Milestone | Task / Deliverable | Owner | Start Date | End Date | Status | % Complete
1.0 | Initiate & Plan Phase | PM Name] | [Date] | [Date] | Completed | 100%
1.1 | Develop & Approve Charter | [PM Name] | [Date] | [Date] | Completed | 100%
1.2 | Develop Project Plan & POAM | [PM Name] | [Date] | [Date] | Completed | 100%
2.0 | Execute Phase: Kiosk Procurement | [Logistics Lead] | [Date] | [Date] | In Progress | 50%
2.1 | Finalize Vendor Selection | [Logistics Lead] | [Date] | [Date] | Completed | 100%
2.2 | Procure & Receive Hardware | [Logistics Lead] | [Date] | [Date] | In Progress | 25%
3.0 | Execute Phase: IT Integration | [IT Lead] | [Date] | [Date] | Not Started | 0%
3.1 | Configure Network Ports | [IT Lead] | [Date] | [Date] | Not Started | 0%
3.2 | Integrate with MHS GENESIS API | [IT Lead] | [Date] | [Date] | Not Started | 0%
… | … | … | … | … | … | …
Status Key: In Progress / On Track | Not Started | At Risk | Overdue | Completed
Notes: TOOL #2 GUIDANCE: THE POAM
Purpose: To decompose large deliverables into manageable tasks and establish your schedule baseline.
The 40-Hour Rule: Break your WBS (Work Breakdown Structure) into tasks that take roughly 40 hours or less to complete. If a task says "Install System" and takes 6 months, break it down further.
Single Ownership: Every task must have ONE owner. If a task has two owners, it has no owners.
Tracking: Once approved, this is your baseline. Update the "% Complete" and "Status" weekly to catch schedule slips early.

## Slide 4: Risk & Issue Register Template
Risk Register
ID | Risk Description | Probability (1-5) | Impact (1-5) | Score (P*I) | Mitigation Strategy | Owner | Status
R-01 | Global supply chain issues delay kiosk hardware delivery by >4 weeks. | 4 | 5 | 20 (High) | Identify alternative vendors and pre-order non-critical components. | [Logistics Lead] | Active
R-02 | Staff resistance leads to low adoption and continued use of manual check-in. | 3 | 4 | 12 (Med) | Involve staff in the planning process; develop a robust change management & training plan. | [PM Name] | Active
R-03 | MHS GENESIS API update breaks integration with kiosks. | 2 | 5 | 10 (Med) | Establish dedicated integration testing environment before rolling out updates. | [IT Lead] | Watching
Issue Log
ID | Issue Description | Date Raised | Action Plan | Owner | Status
I-01 | Kiosk vendor confirmed a 3-week shipping delay for critical touchscreens. | [Date] | Expedite shipping on alternative components to shorten integration timeline. | [Logistics Lead] | In Progress
Risk Score Key: 1-8 (Low) | 9-16 (Medium) | 17-25 (High)
This template is best implemented in Excel or a SharePoint List for automated calculations and notifications.
Notes: TOOL #3 GUIDANCE: RISK & ISSUE REGISTER
Purpose: To look ahead for roadblocks (Risks) and track current fires (Issues).
Risk vs. Issue: A RISK is an uncertain event that might happen (e.g., "Hardware might be delayed"). An ISSUE is an event that has happened (e.g., "Hardware is delayed by 3 weeks").
Mitigation: Do not just list a risk and hope it doesn't happen. Every risk needs a mitigation strategy (Avoid, Transfer, Mitigate, or Accept) and an assigned Owner who is actively monitoring it.
Review Cadence: Do not fill this out once and forget it. Review this slide at the start of every project team meeting.

## Slide 5: Project Status Report Template Project Title:
Project Lead: | Overall Status: (Green: On-Track / Amber: At Risk / Red: Off Track) | Project Lead | As Of Date:
Recent Accomplishments (Last Month/Week): Major completed task or milestone 1 [completion date] Major completed task or milestone 2 [completion date] Major completed task or milestone 3 [completion date] Upcoming Accomplishments/Milestones (Next 4 Weeks): [Planned Date]: Upcoming critical task or milestone 1. [Planned Date]: Upcoming critical task or milestone 2. [Planned Date]: Upcoming critical task or milestone 3. |  | Project Plan. POAM of project milestones and key tasks. | 
Key Performance Indicators. |  | Risk and Issue Mitigation Plan. Insert top 1-3 risks requiring senior leader awareness and mitigation plans. Decisions Required: Include any decisions required by Project Sponsor.s | 
Date Identified | Risk/Issue Description | Risk/Issue Mitigation Plan
Percent Complete: | 0.0%
Total Tasks: | 0
Tasks Complete: | 0
Tasks Overdue: | 0
KPI | Target | Actual Performance | Trend
KPI 1 | 100% |  | 
KPI 2 | <5% |  | 
KPI 3 | XX% |  | 
Notes: TOOL #4 GUIDANCE: STATUS REPORT
Purpose: To provide Project Sponsors with a rapid, 60-second executive summary of project health and value delivery.
Honest Status Indicators (🟢🟡🔴): Do not hide behind Green. If you are behind schedule, mark it Yellow or Red. In project management, "Red" is not a failure; it is a request for leadership help.
Key Performance Indicators (KPIs): Do not just report on activity (e.g., "held a meeting"). Report on value and variance. Are you tracking to your baseline budget and schedule? Are you hitting the adoption metrics you defined in your Charter?
Recent Accomplishments (Look Back): List the top 2-3 tangible deliverables completed since the last report (e.g., "Last 14 days"). Focus on completed milestones, not ongoing administrative tasks.
Upcoming Milestones (Look Ahead): List the critical targets for the next reporting period (e.g., "Next 30 days"). Crucial: Always include the planned target date for these upcoming milestones so leadership knows exactly when to expect them.
Top Risks & Active Issues: Do not list every minor hiccup. Highlight the top 1-2 critical roadblocks threatening the timeline, budget, or quality.
Mitigation Plans & Decisions Required: For every risk or issue listed, you must provide a mitigation action plan. Furthermore, never leave the "Decisions Required" section blank. If you have a roadblock, explicitly state the decision or action you need from the Sponsor to clear it.