## Slide 1: Change Management Toolkit
Welcome to the Change Management Toolkit:
These four templates are designed to be downloaded, customized, and used immediately on your projects.
Do not get bogged down in making them perfect; use them to drive conversations, align your teams, and deliver value.
Notes: HOW TO USE THIS TOOLKIT:
Welcome to the DHA Change Management Toolkit! As a Project Manager or Change Leader, your goal is not just to install a new system or process; your goal is to drive adoption, reduce resistance, and deliver actual mission value to the Defense Health Agency and our patients.
Save a Master Copy: Keep this file clean as your "Master" template. Whenever you start a new initiative, "Save As" and name it for your specific project.
Action-Oriented: These templates are designed to be diagnostic and actionable. Do not use them just to document complaints—use them to create specific mitigation strategies and leadership scripts.
Iterate: The human side of change is dynamic, and resistance will shift over time. Update these assessments and matrices constantly as your stakeholders progress through the transition.

## Slide 2: Organizational Change Readiness Assessment
Readiness Domain | Assessment Criteria (Discuss with Project Leadership) | Score (1 (High Risk / Not Ready) to 5 (Highly Ready)) | Mitigation if Score is <3
1. Strategic Alignment | Is this change explicitly tied to current DHA/DoW strategic priorities (e.g., patient safety, readiness), and is that connection obvious to the front line? |  | Sponsor must draft a clear "Mission Impact" statement before any technical training begins.
2. Leadership Capacity | Do the local commanders/directors have the actual time and bandwidth to be active and visible sponsors for this specific project right now? |  | Delay launch or re-prioritize other local initiatives to free up leadership bandwidth.
3. Change Saturation | How many other major changes (IT rollouts, restructuring, policy shifts) is this specific target audience currently undergoing? |  | Stagger the go-live date to avoid overlapping with other major disruptions.
4. Historical Trust | How did the last major project rollout go? Is there lingering cynicism or a history of "flavor of the month" projects that were abandoned? |  | Acknowledge past failures openly. Focus heavily on early, visible "quick wins" to rebuild trust.
5. Resource Availability | Are the necessary resources (funding, dedicated training time, super-users, help-desk support) secured and protected from competing operational duties? |  | Escalate to Executive Steering Committee; do not launch without protected training time for staff.
Total Score | (A score below 15 indicates a high risk of project failure due to environmental factors, regardless of technical readiness). | / 25 | 
20 - 25 (Green): High Readiness. Proceed with standard change management plan.
15 - 19 (Yellow): Moderate Risk. Proceed with caution; heavy sponsor involvement required.
Below 15 (Red): High Risk. Do not launch technical training. Escalate to Executive Sponsor to stabilize the environment first.
Notes: TOOL #1 GUIDANCE: READINESS ASSESSMENT
• Purpose: To act as a "pre-flight check" to evaluate if your MTF, Network, or Directorate is culturally and operationally ready to absorb the change before deployment begins.
• Be Brutally Honest: When scoring the 5 domains, avoid optimism bias. If you score a 3 or lower in any category, do not ignore it. This is a red flag for project failure and must be mitigated before launch.
• Sponsorship Alignment: Do not fill this out in a vacuum. Use this tool with your Executive Sponsor. It helps them see the environmental risks (like change fatigue or lack of resources) beyond just the technical project schedule.
• The "Go/No-Go" Rule: If the total score is below 15, escalate the results. Recommend pausing the rollout, staggering the schedule, or de-conflicting with other major initiatives until the environment is stabilized.

## Slide 3: Stakeholder Impact & Resistance Matrix
Stakeholder Group | Current State (What they do now) | Future State (What changes) | Level of Disruption (High/Med/Low) | Anticipated Root Cause of Resistance | Mitigation Strategy / Tactic | Owner
Ex: Frontline Nurses & Providers | Charting using legacy system / customized local workflows | Enterprise EHR with standardized fields and mandatory drop-downs | High | Fear that "too many clicks" will slow down patient care; severe change fatigue | Deploy peer "Super Users" for 1-on-1 workflow mapping prior to launch; provide 24/7 at-the-elbow support during week one | Clinical Informaticist / Nursing Champion
Ex: Clinic Admins / Front Desk Staff | Using custom, local scheduling rules and manual check-ins | Standardized enterprise automated check-in kiosks / portals | High | Loss of autonomy and control; feeling like "HQ doesn't know our specific patient needs"; fear of job obsolescence | Involve lead admins in early User-Acceptance Testing (UAT); Sponsor explicitly addresses job security and validates their concerns in town hall | Project Manager & Executive Sponsor
Department Chiefs / Clinic Directors | Pulling readiness/performance data manually into Excel to present to the Commander "their way" | Automated, real-time data dashboard visible directly to MTF Command and HQ | Medium | Fear of transparency; loss of control over the narrative; lack of trust in the new system's data accuracy | Provide a 30-day "Sandbox" period to run both systems in parallel so they can verify data accuracy privately before it goes live to Command | Data Analytics Lead / PM
Notes: TOOL #2 GUIDANCE: STAKEHOLDER RESISTANCE MATRIX
• Purpose: To predict exactly where resistance will occur based on the level of disruption, and to assign targeted mitigation tactics before the friction stalls your project.
• The "WIIFM" Rule: Look at the "Future State" entirely from the stakeholder's perspective. What's In It For Me? If the new process requires more clicks or threatens their autonomy, expect high resistance.
• Tailored Mitigation: Avoid "one-size-fits-all" email blasts. If clinical staff fear patient safety risks, your mitigation tactic must address patient safety directly. If IT staff fear workload burnout, address system stability.
• Tracking: Revisit this matrix at every major project milestone. Are your mitigation tactics actually reducing the disruption? If not, pivot your approach.

## Slide 4: ADKAR® Barrier Diagnostic Assessment
ADKAR Element | Diagnostic Question (Ask the End-User) | Score (1 (Strongly Disagree) to 5 (Strongly Agree)) | PM Action if Score is < 3
Awareness | "I understand why the DHA is implementing this change right now." | 4 | Stop training. Have the Executive Sponsor communicate the business/mission reasons.
Desire | "I am willing to support and participate in this change." | 2 | Find the WIIFM (What's in it for me?). Engage direct supervisors.
Knowledge | "I know exactly how to use the new system or perform the new process." | 1 | Provide formal training and quick-reference guides.
Ability | "I can perform the new tasks at the required level in my actual daily environment." | 1 | Deploy Super Users and provide at-the-elbow support.
Reinforcement | "I receive recognition and see metrics that prove we are not going back to the old way." | 1 | Celebrate early wins and ensure leaders are walking the floor.
Highlight the FIRST row that scores a 3 or lower in RED. This is your Barrier Point. Stop and address this element before moving to the next
Notes: TOOL #3 GUIDANCE: ADKAR BARRIER DIAGNOSTIC
• Purpose: To pinpoint the exact psychological barrier (Awareness, Desire, Knowledge, Ability, Reinforcement) that is stalling adoption for a specific group of users.
• The Sequential Rule: The ADKAR model is strictly linear. You cannot train (Knowledge) someone who doesn't want the change (Desire). Stop pushing forward and address the very first element that scores a 3 or lower.
• Survey Deployment: Send this out as a quick, 5-question pulse-check survey to impacted staff, or use it as a structured discussion guide in small focus groups.
• Action: Tie the results directly to your project plan. If 'Ability' is scoring low two weeks after go-live, immediately deploy your Super Users for at-the-elbow support.

## Slide 5: Sponsor Action & Communication Plan
Project Phase | Key Message Focus | Sender (Who says it) | Channel / Activity | Date / Milestone | Status (Not Started, On Track, Complete)
Pre-Launch | The Urgency & "Why we must change." | Executive Sponsor | Town Hall / All-Hands Meeting | [Date] | On Track
Pre-Launch | "What this means for our specific team." | Direct Supervisor | Small Group Team Meeting | [Date] | On Track
Implementation | "Here is the training and support plan." | Project Manager | Email / LMS / Workshops | [Date] | Not Started
Go-Live | Visible presence and barrier removal. | Executive Sponsor & Supervisors | "Walking the floor" | [Date] | Not Started
Post-Launch | "Look at our success. We are not going back." | Executive Sponsor | Dashboard review / Public Recognition | [Date] | Not Started
Purpose: To give PMs a template to hand to their sponsors, detailing exact actions and messages.
Notes: TOOL #4 GUIDANCE: SPONSOR ACTION PLAN
• Purpose: To equip your Executive Sponsors and Direct Supervisors with the exact script, timeline, and actions they need to drive adoption. Sponsors want to help, but they need you to tell them how.
• The Sender Rule: Employees want to hear the business "Why" (Strategic alignment, Mission Impact) from Executives. But they want to hear the personal "How does this affect my job" from their Direct Supervisor. Do not mix these up.
• Active & Visible: A memo is not sponsorship. Ensure the "Channel / Activity" column includes physical or virtual presence—schedule town halls, floor walks, and live dashboard reviews.
• Tracking: Treat these communication milestones exactly like technical deliverables on your POAM. If the Executive Sponsor misses a critical town hall, the project is off schedule.